BLUECASH PROTOCOL

Implementation & Merge Guide

Week-by-week, step-by-step build instructions for each engineer, plus the branching and merge workflow that keeps the shared Rust core, the Android client, and the backend in sync.

Companion to the Final Proposal — September 2026

# 1. Repository Layout

Both people work out of one monorepo so the crate's interface, the Android app, and the backend stay easy to cross-reference in review.

bluecash/

├── crates/

│   └── bluecash-crypto/     # shared Rust core — Person A owns

│       ├── src/

│       ├── uniffi/           # interface definition (.udl or proc-macro)

│       └── Cargo.toml

├── backend/                  # FastAPI app — Person A owns

├── mobile/                   # Kotlin/Compose app — Person B owns

├── scripts/

│   └── integration_test.sh   # run at every joint checkpoint

└── infra/                    # Docker Compose, CI workflows

# 2. Person A — Rust Core & Backend: Step by Step

## Week 1 — Setup & Threat Model

- Scaffold the crate: `cargo new --lib crates/bluecash-crypto`, add it as a workspace member in the root `Cargo.toml`.

- Add dependencies: `ed25519-dalek`, `x25519-dalek`, `aes-gcm`, `sha2`, `bbs-plus`, `sharks`, `rs_merkle`, `uniffi`, `pyo3`.

- Write the crate's public interface first — function signatures only, no bodies — covering keygen, sign/verify, ECDH, AES-GCM, blind-sign request/issue/unblind, BBS+ issue/prove/verify, Shamir split/evaluate/reconstruct, and Merkle build/proof/verify.

- Write the UniFFI interface definition mirroring those signatures — this is the contract Person B builds against from Week 2 onward. Circulate it for sign-off before writing implementations.

- Scaffold the PyO3 module (`#[pymodule]`) wrapping the same functions.

- Set up CI: one job cross-compiles the crate for `aarch64-linux-android` via `cargo-ndk`, another builds the Python wheel via `maturin`. Both run on every push touching `crates/bluecash-crypto`.

- Scaffold the FastAPI app with a health-check endpoint, async Postgres connection, and an Alembic migration for the wallet/token/receipt schema.

- Bring up Docker Compose with Postgres and the backend service.

## Week 2 — Key Management & Core Primitives

- Implement Ed25519 keypair generation, signing, and verification using `ed25519-dalek`.

- Implement the X25519 key exchange with an HKDF-derived AES-256-GCM session key.

- Run `uniffi-bindgen generate` and confirm the generated Kotlin API matches the interface frozen in Week 1.

- Build the Python wheel locally with `maturin develop`; write unit tests for the sign/verify and ECDH round-trip.

- Implement `POST /mint/registerDevice`, verifying the device's Ed25519 signature via the crate.

## Week 3 — Minting Flow (Blind Signatures)

- Implement the blind-signature scheme in the crate: `blind_sign_request` (client blinds), `blind_sign_issue` (Mint signs the blinded value), `unblind` (client unblinds).

- Write a property-based test confirming an unblinded signature verifies against the original, unblinded message.

- Implement `POST /mint/issue`, calling `blind_sign_issue`.

## Week 4 — BLE Discovery & Pairing (joint checkpoint)

- Implement Merkle tree build/proof/verify using `rs_merkle`.

- Implement `GET /audit/root/latest`.

- Run `scripts/integration_test.sh --stage pairing` against Person B's branch (see Section 4).

## Week 5 — Secure Channel & Anonymous Auth

- Implement BBS+ credential issuance and verification using `bbs-plus`.

- Implement a StrongBox/Play-Integrity attestation-verification endpoint on the backend.

## Week 6 — Token Transfer Protocol (joint checkpoint)

- Implement batch issuance and publish the resulting Merkle root via `/audit`.

- Freeze the token JSON schema jointly with Person B.

- Run `scripts/integration_test.sh --stage pay-flow`: mint → issue → verify Merkle inclusion end-to-end.

## Week 7 — Double-Spend Detection

- Implement `shamir_evaluate` and `shamir_reconstruct` (Lagrange interpolation) in the crate — both platforms use the same implementation.

- On receipt upload, detect repeated `token_id` values with distinct `n_ctx` and call `shamir_reconstruct` to recover the cheating identity.

## Week 8 — Settlement Sync (joint checkpoint)

- Implement `POST /settlement/uploadBatch`.

- Implement the reconciliation job that marks tokens settled and updates the ledger.

- Run `scripts/integration_test.sh --stage settlement`: full settlement round-trip.

## Week 9 — Fraud & Audit Engine

- Implement `POST /fraud/report` finalization and revocation push (adds the recovered identity to the Mint's revocation accumulator).

- Implement the Audit Engine's public verification endpoint.

## Week 10 — Polish & Field Demo (joint checkpoint)

- Load-test the backend with ~1,000 simulated transactions.

- Write the security section of the final report (threat-model coverage, primitive choices, known limitations).

- Run `scripts/integration_test.sh --stage full` and confirm both CI jobs are green on the release tag before the demo.

# 3. Person B — Android & Client Integration: Step by Step

## Week 1 — Setup & Threat Model

- Create the Android Studio project (Kotlin, Jetpack Compose, min SDK matching the BLE APIs in use).

- Set up the Gradle module structure with a package reserved for generated UniFFI bindings.

- Add BLE permissions to the manifest and build the runtime permission-request flow.

- Build the Compose navigation shell (Wallet home, Pay, Receive, Settings placeholders).

- Review and sign off on the crate interface Person A circulates at the end of Week 1.

## Week 2 — Key Management & Core Primitives

- Pull the generated bindings and native library from Person A's CI, or build locally:

cargo ndk -t arm64-v8a -t x86_64 -o app/src/main/jniLibs build --release

uniffi-bindgen generate --language kotlin --out-dir app/src/main/java/.../crypto/generated

- Generate the device's hardware-backed Keystore/StrongBox keypair, and the protocol Ed25519 keypair via the Rust core; store private key material behind the Keystore-backed wrapper where possible.

- Build the key-management UI (public key / device ID / registration status).

- Call `POST /mint/registerDevice` from the client.

## Week 3 — Minting Flow (Blind Signatures)

- Build the Deposit/Mint Compose screen (amount entry, Deposit action).

- Call the crate's `blind_sign_request` to blind the token request, POST to `/mint/issue`, call `unblind` on the response, and store the resulting token.

## Week 4 — BLE Discovery & Pairing (joint checkpoint)

- Implement merchant (peripheral) and payer (central) BLE roles with native `BluetoothGatt` or the Nordic Android-BLE-Library: GATT service UUID advertising and scan/filter.

- Implement LE Secure Connections pairing with Numeric Comparison, plus a QR (CameraX + ZXing) out-of-band fallback.

- Run the pairing stage of `scripts/integration_test.sh` against two emulators or devices.

## Week 5 — Secure Channel & Anonymous Auth

- Implement the X25519 ECDH exchange and AES-256-GCM channel setup via the Rust core; discard the session key immediately after each transaction.

- Implement on-device BBS+ proof generation (`bbs_prove`) using the credential issued by Person A's endpoint.

- Implement the RSSI/latency distance-bounding check around the pairing handshake.

## Week 6 — Token Transfer Protocol (joint checkpoint)

- Build the Pay/Receive Compose screens.

- Set up the local encrypted ledger: Room + SQLCipher-for-Android (or Jetpack Security EncryptedFile), hash-chained per the original protocol spec.

- Implement client-side Merkle inclusion-proof verification (`merkle_verify`) before accepting a token.

- Freeze the token schema jointly with Person A; run the pay-flow integration test.

## Week 7 — Double-Spend Detection

- Build the spend context `n_ctx` and call the crate's `shamir_evaluate`; attach the `revealed_share` to the outgoing receipt.

- Implement the local same-merchant Bloom filter natively in Kotlin (small, dependency-free implementation is sufficient at MVP scale).

## Week 8 — Settlement Sync (joint checkpoint)

- Implement background sync via WorkManager: batch signed receipts and upload to `/settlement/uploadBatch` when connectivity returns.

- Run the settlement stage of the integration test across two devices through to backend reconciliation.

## Week 9 — Fraud & Audit Engine

- Build a minimal fraud/status screen showing revocation state pulled from the Audit Engine's public endpoint.

## Week 10 — Polish & Field Demo (joint checkpoint)

- Complete a UI polish pass across all screens.

- Wire Play Integrity checks at app start and before sensitive operations (minting, first pairing).

- Run a low-connectivity field test: airplane mode, BLE only, full pay flow.

- Join the final field demo and confirm the release-tagged build is what's demoed.

# 4. Branching & Merge Workflow

Trunk-based development off `main`. Three branch prefixes keep ownership clear without blocking either person on the other's day-to-day work:

| Prefix | Owner | Merge requirement |
| --- | --- | --- |
| core/* | Person A (crate changes) | Rust unit tests + both CI cross-compiles green; Person B reviews if the public interface changes |
| backend/* | Person A | Backend test suite green |
| android/* | Person B | Android build green; instrumented tests pass on emulator |

## Versioning the shared crate

Every crate change that touches the public interface gets a semver tag, e.g.:

git tag crypto-v0.3.0 && git push --tags

Both `backend/` and `mobile/` pin to a specific tag rather than tracking the crate's HEAD, so a change on one side can't silently break the other mid-week. The pin is bumped deliberately, only after an integration test passes — see the checkpoint procedure below.

## Checkpoint procedure — Weeks 4, 6, 8, 10

- Person A tags the crate at its current state once that week's crate work is merged to `main` (e.g. `crypto-v0.4.0`).

- Person B bumps `mobile/`'s dependency pin to that tag, regenerates bindings (`uniffi-bindgen generate` + `cargo ndk build`), and merges any pending `android/*` branches on top.

- Both run `scripts/integration_test.sh --stage <week-stage>` against a local backend + emulator/device pair — the script exercises that week's specific flow (registration+pairing at Week 4, full pay flow at Week 6, settlement at Week 8, full end-to-end + load at Week 10).

- If the test passes, `backend/*` and `android/*` branches merge to `main`. If it fails, it's triaged the same day — the whole point of the checkpoint is to catch drift before it compounds into the following week.

## Final merge — after Week 10

- Freeze the crate interface and tag the final release: `crypto-v1.0.0`.

- Merge the final `android/*` and `backend/*` branches to `main` once each passes the full integration and load test suite.

- Build release artifacts: signed release APK (`./gradlew assembleRelease`), and a multi-stage backend Docker image (compile the crate → build the Python wheel → build the FastAPI image).

- Tag the repository `v1.0.0-mvp`.

- Run the field demo against the tagged release artifacts — not against `main` — so the demo matches exactly what's tagged.

- Reference the tagged commit hash in the final security / IEEE write-up for reproducibility.

BlueCash Protocol — Implementation & Merge Guide | Companion to the Final Proposal | September 2026